## Slide 1: From single project RCPSP to multi-project multi-mode RCPSP

## Slide 2: Single project RCPSP
, I is the dummy end task
s.t.
-,
rR, t = {0,1,2,…,T}
Decision variables
{0,1}, , t=
Based on
Karamlou and Bocchini. (2016). From component damage to system-level probabilistic restoration functions for damaged bridges.

## Slide 3
X= [] =
Vector size of decision variables
[(T+1) I] 1
Mixed-integer linear programming solver
[X, fval, exitflag] = intlinprog (f, intcon, A, b, Aeq, beq, lb, ub);
f, x, intcon, b, beq, lb, and ub are vectors, and A and Aeq are matrices.

## Slide 4: multi-mode RCPSP
-,
rR, t = {0,1,2,…,T}
{0,1}, , , t=
s.t.
Precedence constraint

## Slide 5
X= [] =
Vector size of decision variables
[(T+1) (+)] 1
Mixed-integer linear programming solver
[X, fval, exitflag] = intlinprog (f, intcon, A, b, Aeq, beq, lb, ub);
f, x, intcon, b, beq, lb, and ub are vectors, and A and Aeq are matrices.

## Slide 6
task # | 1st Mode |  | 2nd Mode | 
 | duration | Resource usage | duration | Resource usage
1 | 0 | 0 | 0 | 0
2 | 4 | 2 | 6 | 1
3 | 2 | 1 | 2 | 1
4 | 3 | 3 | 5 | 1
5 | 2 | 1 | 2 | 1
6 | 2 | 2 | 4 | 1
7 | 0 | 0 | 0 | 0
Renewable resource available per period = 6
0.006412 seconds
Renewable resource available per period = 4
0.012903 seconds

## Slide 7
Project 1
Project 2
Project 3
Project 4
Project 5
task # | 1st Mode |  | 2nd Mode | 
 | Duration | Resource | Duration | Resource
1 | 0 | 0 | 0 | 0
2 | 0 | 0 | 0 | 0
3 | 3 | 3 | 2 | 1
4 | 5 | 2 | 4 | 2
5 | 6 | 3 | 1 | 2
6 | 2 | 4 | 3 | 1
7 | 0 | 0 | 0 | 0
8 | 0 | 0 | 0 | 0
9 | 1 | 5 | 3 | 3
10 | 5 | 3 | 2 | 3
11 | 5 | 2 | 1 | 3
12 | 3 | 1 | 1 | 1
13 | 2 | 3 | 2 | 1
14 | 0 | 0 | 0 | 0
15 | 0 | 0 | 0 | 0
16 | 2 | 2 | 2 | 2
17 | 6 | 3 | 2 | 2
18 | 3 | 3 | 2 | 1
19 | 3 | 3 | 3 | 2
20 | 0 | 0 | 0 | 0
21 | 0 | 0 | 0 | 0
22 | 2 | 2 | 1 | 2
23 | 4 | 2 | 3 | 2
24 | 4 | 3 | 1 | 2
25 | 2 | 3 | 1 | 1
26 | 3 | 3 | 2 | 1
27 | 0 | 0 | 0 | 0
28 | 0 | 0 | 0 | 0
29 | 1 | 2 | 2 | 1
30 | 2 | 2 | 3 | 2
31 | 6 | 1 | 1 | 3
32 | 3 | 3 | 2 | 1
33 | 0 | 0 | 0 | 0
34 | 0 | 0 | 0 | 0
Renewable resource available per period = 6
3.102517 seconds

## Slide 8
Project 1
Project 2
Project 3
Project 4
Project 5
task # | 1st mode |  | 2nd mode | 
 | Duration | Resource | Duration | Resource
1 | 0 | 0 | 0 | 0
2 | 0 | 0 | 0 | 0
3 | 3 | 3 | 2 | 1
4 | 5 | 2 | 4 | 2
5 | 6 | 3 | 1 | 2
6 | 2 | 4 | 3 | 1
7 | 0 | 0 | 0 | 0
8 | 0 | 0 | 0 | 0
9 | 1 | 5 | 3 | 3
10 | 5 | 3 | 2 | 3
11 | 5 | 2 | 1 | 3
12 | 3 | 1 | 1 | 1
13 | 2 | 3 | 2 | 1
14 | 0 | 0 | 0 | 0
15 | 0 | 0 | 0 | 0
16 | 2 | 2 | 2 | 2
17 | 6 | 3 | 2 | 2
18 | 3 | 3 | 2 | 1
19 | 3 | 3 | 3 | 2
20 | 0 | 0 | 0 | 0
21 | 0 | 0 | 0 | 0
22 | 2 | 2 | 1 | 2
23 | 4 | 2 | 3 | 2
24 | 4 | 3 | 1 | 2
25 | 2 | 3 | 1 | 1
26 | 3 | 3 | 2 | 1
27 | 0 | 0 | 0 | 0
28 | 0 | 0 | 0 | 0
29 | 1 | 2 | 2 | 1
30 | 2 | 2 | 3 | 2
31 | 6 | 1 | 1 | 3
32 | 3 | 3 | 2 | 1
33 | 0 | 0 | 0 | 0
34 | 0 | 0 | 0 | 0
Renewable resource available per period = 8
1.137673 seconds